# Terms of Reference

# Appointment of Contractor to carry out

# (A) Interim Evaluation for the InterTradeIreland Synergy Programme Phase II

# FOLLOWED BY

# (B) Economic Appraisal of the InterTradeIreland Synergy Programme Phase III

Introduction

InterTradeIreland is the All-Island Trade and Business Development Body, one of six North South Implementation Bodies established under the Good Friday Agreement. In this capacity, it acts as the All-island Economic Development Agency. It is funded by the Department of Enterprise, Trade and Employment (DETE) in Ireland and the Department for the Economy (DfE) in Northern Ireland.

InterTradeIreland is the only organisation that has been given responsibility by both governments to boost North-South economic cooperation to the mutual benefit of Ireland and Northern Ireland.  The agency’s remit is to ‘exchange information and coordinate work on trade, business development and related matters, in areas where the two administrations specifically agree it would be in their mutual interest.

InterTradeIreland achieves its legislative remit through several means, including:

- Connecting and helping businesses across the island to trade cross-border, collaborate, innovate and attract investment.

- Business and economic research which provides insight and foresight for policy makers and a robust evidence base to design initiatives that support businesses.

- Collaboration with stakeholders across the island to fulfil its unique role to accelerate economic growth through the identification and delivery of shared policy priorities in both jurisdictions.

InterTradeIreland’s Corporate Plan 2023 – 2025 outlines the agency’s ambition:

Vision: A globally competitive all-island business ecosystem that advances both economies

Mission: To provide leadership, advice, and support to maximise export growth opportunities through greater Cross-Border collaboration, innovation, entrepreneurship, and trade.

InterTradeIreland’s strategic priorities are aligned to the economic and enterprise policy priorities pursued by its Sponsor/Partner departments in areas such as innovation, decarbonisation, and boosting productivity among SMEs.

Background

The Synergy Programme Phase II, formally approved by the InterTradeIreland Board in March 2023, is an initiative aimed at enhancing cross-border collaboration between SMEs, academics, policymakers, corporates, and third-sector participants. Synergy’s core objective is to foster innovative networks that promote economic growth and mutual benefit for Ireland and Northern Ireland.

The programme specifically seeks to:

- Activate SMEs and relevant organisations to participate in cross-border clusters and networks.

- Leverage networks to solve common challenges and identify joint opportunities across both jurisdictions.

- Scale collaboration through cluster development supports, increasing the impact of innovation and economic initiatives across the island.

The framework for Synergy is built around the POPPS (Problem, Opportunities, People, Pathway, Solution) approach, encouraging problem-solving and opportunity identification in collaboration with strategic partners across Ireland and Northern Ireland. This alignment supports InterTradeIreland’s corporate goals of promoting economic collaboration between the two regions.

Priority outputs of the programme include:

- Increasing SME productivity.

- Assisting the transition to a low-carbon economy.

- Embracing Industry 4.0 technologies.

- Facilitating SME engagement in cross-border clusters and networks.

Target sectors such as the Bio-Economy, Cyber Security, Advanced Manufacturing, and Life Sciences are strategically chosen for their potential to drive cross-border cooperation and deliver mutual economic value. These sectors align with broader regional strategies and policies, offering significant opportunities for both Ireland and Northern Ireland.

The Synergy Programme contributes to the development of modern innovation systems, fostering collaborations that build on sectoral strengths, identify new growth opportunities, and enhance economic resilience. It also addresses key market and system failures in innovation, supporting coordinated responses to industry needs while promoting cross-border knowledge exchange, technology adoption, and skills development.

In line with InterTradeIreland’s Corporate Plan (2023-2025), Synergy plays a critical role in scaling cross-border business linkages, fostering collaborative innovation, and supporting clusters that drive entrepreneurship and economic growth. Through its structured objectives, Synergy supports 7 cross-border projects per year and aligns with InterTradeIreland’s goals to grow exports and strengthen cross-border network.

Synergy Support

The Synergy Programme is designed to foster cross-border collaboration between organisations in Ireland and Northern Ireland, with a focus on solving common problems or capitalising on joint opportunities. The programme requires participants to demonstrate a tangible impact in both regions, aligning with InterTradeIreland’s Corporate Plan. InterTradeIreland aims to support collaborations that benefit SMEs by developing strategic partnerships with economic development agencies, industry bodies, and private sector partners to address market failures and create economic opportunities.

Synergy supports a wide range of activities, including training initiatives, matchmaking, mapping projects, online portals, salary costs, event costs (such as conferences), and commercially focused research and publications. The programme is open to innovative pathways addressing specific issues, with participants encouraged to engage with the InterTradeIreland Innovation and Entrepreneurship Team early in the process to discuss proposals.

Programme Management

The Synergy Programme is be managed by InterTradeIreland’s existing Synergy Team. While the core Synergy Team is primarily responsible for programme delivery, other InterTradeIreland team members may also contribute. Due to the strategic importance of Synergy in achieving ITI’s corporate objectives, it is anticipated that all client-facing staff will play a role in promoting the programme. These staff members may also support project management, particularly when they have pre-established relationships with stakeholders involved in cross-border network collaboration projects.

This approach is expected to enhance relationship-building and trust between networks, enabling smoother and more timely project execution.

Objectives of the Synergy Programme

The Synergy Programme aims to contribute to several strategic objectives outlined in InterTradeIreland’s Corporate Plan (2023-2025), including:

- Strengthening all-island clusters and networks.

- Increasing SME participation in clusters and networks.

- Promoting a vibrant entrepreneurship ecosystem and increasing the number of investor-ready businesses

- Enhancing business engagement in innovation and collaboration.

- Leading and facilitating collaboration activities to benefit SMEs.

- Brokering and funding cross-border cluster and network connection

- Increasing cross-border exports and the number of exporters.

The programme aligns with InterTradeIreland’s broader goals of fostering innovation and economic growth through cross-border collaboration.

Outputs of the Synergy Programme

The primary outputs of the Synergy Programme are aimed at supporting economic growth across Ireland and Northern Ireland through:

- Strengthened cross-border networks and clusters.

- Increased SME participation in collaborative innovation activities.

- Enhanced cross-border business connections, facilitating exports and entrepreneurship.

- Development of all-island sectoral ecosystems that address shared challenges and opportunities.

Through its diverse supports, Synergy enables the creation of lasting partnerships that drive innovation and contribute to the economic resilience of both Ireland and Northern Ireland.

# Terms of Reference

# (A) Interim Evaluation review for the InterTradeIreland Synergy Programme Phase II

InterTradeIreland invites proposals for a consultant to deliver an Interim Evaluation of its Synergy Programme Phase II.

The Synergy Programme Phase II is a cross-border initiative aimed at fostering all-island innovation clusters to drive economic growth. This interim evaluation will assess how effectively the programme is delivering its intended outcomes and value for money, while examining the efficiency of its delivery model and ensuring alignment with strategic policy objectives.

The appointed consultant will provide evidence-based insights and recommendations to inform improvements, strengthen governance, and enhance accountability for future programme phases.

Objectives of the Interim Evaluation

The evaluation should address the following key objectives, maintaining focus on outcomes, value for money, and good governance:

- Assess the effectiveness of Synergy Phase II in meeting its objectives and SMART targets, with reference to the POPPS framework (Problem, Opportunities, People, Pathway, Solution). Determine the extent to which intended outcomes are being achieved and identify any shortfalls.

- Review the appropriateness and efficiency of the current delivery model including governance structures, operational processes, and resource allocation.

- Confirm alignment of Synergy Phase II with InterTradeIreland’s corporate strategy, relevant North–South government policies, and the wider all-island innovation and cluster development ecosystem. Ensure the programme remains in step with overarching policy goals and complements other initiatives.

- Identify evidence-based recommendations for improvement. Highlight opportunities to enhance programme outcomes, increase value for money, and strengthen governance and accountability mechanisms in any future phase.

Scope of Work

Key Stages and Tasks

To achieve the above objectives, the consultant will undertake the following key stages and tasks:

1. Programme Performance Assessment

- Review the programme’s performance to date against its original objectives, SMART targets and the POPPS framework. Assess which problems and opportunities the programme has addressed, how stakeholders have been engaged, what pathways have been implemented, and what solutions have been delivered.

- Validate the rationale for funded cluster projects, and assess the impact they have delivered. This should include measuring outputs and outcomes achieved by participants and determining how these contribute to the programme’s objectives.

- Analyse uptake and participation levels across the programme, including the geographic and sectoral spread of clusters and SMEs involved. Identify any under-represented regions or sectors and consider reasons for variances in engagement.

2. Delivery Model Review

- Evaluate the effectiveness of programme management and operational processes. This includes reviewing the end-to-end participant journey from initial enquiry through to project completion and assessing whether timelines and processes are efficient and user-friendly.

- Review the governance arrangements overseeing Synergy Phase II and the decision-making processes in place. Highlight opportunities to improve programme governance, enhance accountability, and streamline operations for better results.

3. Stakeholder Engagement

Conduct primary research with programme stakeholders and beneficiaries across Northern Ireland and Ireland. This should involve engagement with a minimum of 30 individuals or organisations (e.g. cluster leads, participating SMEs, industry networks, academic partners). This should include:

- A combination of surveys and interviews to gather feedback on stakeholders and beneficiaries’ experiences, elicit views on the programme’s delivery effectiveness, the relevance of its targeting and communications, and any barriers encountered.

- Gather qualitative insights into stakeholders and beneficiaries’ satisfaction, perceived benefits and suggestions for improvement. Ensure that feedback from both jurisdictions (North and South) is captured and reflected, identifying any differences in experiences or outcomes.

4. Impact and Success Measures

- Assess the outputs and outcomes of Synergy Phase II against the benchmarks and targets established in the 2023 economic appraisal. Evaluate how the programme’s results contribute to InterTradeIreland’s key performance indicators (KPIs) and wider economic development objectives.

- Capture qualitative impacts of the programme, such as case studies or success stories that illustrate how Synergy Phrase II is making a difference for participants (e.g. new collaborations formed, innovation outcomes, or business growth attributable to the programme).

- Determine the overall effectiveness and value for money of the programme to date.

5. Comparative Analysis

- Examine how Synergy Phase II fits within InterTradeIreland’s broader innovation and entrepreneurship support portfolio. Identify any overlaps or synergies with other InterTradeIreland programmes (for example, Innovation Boost, Acumen, or other cluster support initiatives).

- Map Synergy’s objectives and activities against other active cluster development programmes on the island of Ireland (both North and South). Identify any duplicate activities and highlight gaps where Synergy may not be addressing certain needs that other programmes cover (or vice versa).

- Based on the comparative review, recommend adjustments or enhancements for any future phase of Synergy. This may include opportunities for better coordination with other initiatives, refining the programme’s niche focus, or addressing gaps to ensure a more coherent all-island cluster support ecosystem.

Required Outputs

The consultant will be expected to deliver the following outputs to a high standard, within an agreed format and timeframe:

- A comprehensive written report detailing all findings from the interim evaluation. This report must include analysis of each of the objectives and key tasks outlined above, supported by evidence. It should provide clear conclusions and recommendations for programme enhancement, with a focus on improving outcomes and achieving better value for money.

- The report should include a concise executive summary highlighting the evaluation’s key findings, conclusions, and recommendations. This should be suitable for senior management and governance bodies, providing a quick overview of performance and improvement areas without delving into technical detail.

All deliverables should be produced to a professional standard and delivered by the agreed deadlines.

Evidence of robust analysis should underpin all recommendations to ensure credibility and support effective decision-making for the programme’s future.

Format and Compliance

- The Interim Evaluation proposed must reflect best practice in public-sector evaluation – for example, adherence to the NI Guide to Expenditure Appraisal and Evaluation (NIGEAE) and the Better Business Cases NI framework where relevant to ensure a robust, evidence-based approach.

- The successful consultant will be expected to perform the evaluation in an impartial and transparent manner. Strong emphasis is placed on outcome-focused evaluation, value for money considerations, and adherence to high standards of governance and accountability.

- The evaluation will include reference to, and consultation with, all relevant organisations, including but not limited to:

- Clusters, networks and academics engaged in Synergy Phase II

- InterTradeIreland Senior Leadership Team

- InterTradeIreland Synergy Programme Delivery Team

- Invest Northern Ireland

- Enterprise Ireland

# Terms of Reference

# (B) Economic Appraisal of Synergy Programme Phase III

Building on the successes and lessons of the Interim Evaluation of Phase II, InterTradeIreland is seeking consultancy support to conduct an Economic Appraisal of the Synergy Programme Phase III to assess the feasibility of a further phase of the Synergy Programme in accordance with Better Business Cases NI guidance.

Phase III aims to further scale cross-border collaboration and increase SME participation in all-island clusters.

The appointed consultant will assess the feasibility and economic value of proceeding with Phase III, in accordance with Better Business Cases NI guidance and using the Five Case Model framework.

The economic appraisal will utilise the POPPS framework as a lens for analysis, i.e. articulate the core Problem that Phase III addresses, the Opportunities available, the People (stakeholders/partners) involved, the Pathway for delivery, and the Solution being proposed.

This framework (already embedded in Synergy’s design) will help ensure the appraisal covers all critical dimensions of the programme.

Objectives of the Economic Appraisal

The appointed consultant will complete a comprehensive economic appraisal addressing the following key areas:

- Set out the strategic case for Synergy Phase III by analysing the policy context in Northern Ireland and Ireland.  Evidence the market failures the programme is intended to address and demonstrate how Phase III aligns with relevant government objectives.

- Develop specific SMART targets (Specific, Measurable, Achievable, Relevant, Time-bound) for Synergy Phase III and key performance indicators aligned with InterTradeIreland’s draft corporate plan (2026–2028).

- Ensure that these targets and performance indicators can be realistically measured and tracked over the programme’s lifespan.

- Ensure that lessons learned and recommendations from the Interim Evaluation Synergy Phase II, are embedded across the proposed approach to Synergy Phase III.

- Articulate the demand for Phase III and Synergy’s distinctive role within the wider clustering and innovation ecosystem, ensuring complementarity with, and non-duplication of, other supports.

- Develop and appraise a range of viable delivery options for Phase III and assess a preferred option and demonstrate value for money.

- Translate the preferred option into a commercial and delivery approach and how this approach should be taken forward for Synergy Phase III.

- Prepare the financial case for Phase III, including high-level cost projections for the preferred option.

- Ensure the appraisal addresses relevant State Aid and/or UK Subsidy Control requirements.

Stakeholder Engagement

Stakeholder consultation is expected as part of this economic appraisal. The consultant should engage with relevant stakeholders to gather insights and ensure the appraisal is grounded in practical experience. At minimum, consultations should include:

- InterTradeIreland Senior Leadership Team, to understand strategic priorities, internal perspectives on Synergy’s performance and alignment with corporate objectives.

- InterTradeIreland Synergy Programme Delivery Team.

- A selection of clusters, networks, SMEs, academic or third-sector partners that have been involved in Synergy Phase II.

- Economic development agencies on the island of Ireland: Invest Northern Ireland and Enterprise Ireland.

- Other relevant organisations e.g. industry associations, regional economic development initiatives, or cluster support programs that intersect with Synergy’s objectives.

Tender responses should outline a clear consultation plan, including the proposed methods for stakeholder engagement (e.g. interviews, surveys).

Scope of Work

A complete, economic appraisal report, structured to Better Business Cases NI standards should incorporate all elements outlined below, and delivered within the specified timeframe.

The economic appraisal should include the following sections.

Executive Summary

- Provide a concise overview of the economic appraisal’s purpose, options assessed, key findings, and the recommended Phase III proposal.

- Highlight the strategic rationale, Synergy’s unique position within the ecosystem, and the value-for-money case for the preferred option.

Introduction

- Introduce the Synergy Programme, summarising Phase II interim evaluation outcomes and insights. Set out the rationale for considering Phase III, the economic appraisal scope and methodology.

- Confirm alignment with InterTradeIreland’s corporate priorities and relevant government policies.

- Include a brief description of the stakeholder consultation process that informs the economic appraisal.

- Strategic Case

The Strategic Case should clearly establish the need for Synergy Phase III and its strategic fit.

In developing the Strategic Case, the consultant should:

- Demonstrate how Phase III contributes to relevant policy frameworks, including but

not limited to:

  - The InterTradeIreland Draft Corporate Plan 2026-2028

  - N.I. Programme for Government 2024-2027, Department for the Economy

  - Draft Industrial Strategy for Northern Ireland Economy 2030, Department for the Economy

  - 10x Economy (The Four Pillar Economic Vision), Department for the Economy

  - Delivering Economic Action Plan 2024/25, 3-year forward look, Department for the Economy

  - Skills Action Plan for Northern Ireland 2025, Department for the Economy

  - Enterprise 2030, Department of Enterprise, Trade and Employment

  - Impact 2030: Ireland’s Research and Innovation Strategy, Department of Further and Higher Education, Research, Innovation and Science

  - Development of an Evidence Base to Support the Development of a National Clustering Policy and Framework, Grant Thorton

  - Clustering on the Island of Ireland: A Gap Analysis, InterTradeIreland

  - Synergy Programme Phrase II Economic Appraisal, InterTradeIreland

- Examine demand for Phase III, drawing on the Interim Evaluation of Phase II findings, participant feedback and stakeholder insights.

- Assess Synergy’s distinctive role within the wider innovation and clustering ecosystem across the island of Ireland.

- Set clear, measurable programme objectives for Phase III, including SMART targets informed by Phase II interim evaluation, performance and relevant policy priorities.

2. Economic Case

The Economic Case should determine how Phase III’s objectives can be delivered most effectively and efficiently.

In developing the Economic Case, the consultant should:

- Identify a range of delivery options, including a baseline “do nothing / do minimum” option, and develop a shortlist of viable alternatives representing realistic delivery scales.

For each shortlisted option, the consultant should:

- Carry out a cost–benefit analysis, including Net Present Value (NPV) calculations.

- Quantify economic costs and benefits where feasible (e.g. collaboration outcomes, innovation outputs, longer-term regional impacts).

- Assess qualitative impacts such as enhanced cluster capability, network effects, and alignment with sustainability and regional development objectives.

- Identify and justify the option that offers the best value for money and most effectively meets the objectives of Phase III.

3. Commercial Case

The Commercial Case should explain how the preferred option can be delivered in practice.

In developing the Commercial Case, the consultant should:

- Describe what Phase III will deliver, including the planned support offering and the expected outputs (e.g. types and scale of support, and the indicative number and nature of cluster initiatives supported).

- Set out the high-level delivery model, informed by lessons from Phase II, including any proposed enhancements to application, assessment and related process requirements.

- Assess commercial viability of Synergy Phase III

- Identify key commercial risks and propose appropriate mitigation measures.

4. Financial Case

The Financial Case should confirm the affordability and financial sustainability of the proposed programme.

In developing the Financial Case, the consultant should:

- Provide high-level cost projections for the preferred option (e.g. programme management, support packages, operational costs, marketing, monitoring and evaluation).

- Assess the overall affordability of Phase III over its duration.

- Outline key financial risks and propose appropriate mitigation measures.

5. Management Case

The Management Case should set out how Phase III will be governed, managed and successfully delivered.

In developing the Management Case, the consultant should:

- Outline proposed governance structures, roles and responsibilities.

- Provide a high-level implementation plan covering programme launch, key delivery milestones, monitoring and evaluation.

- Reflect lessons learned from Phase II in relation to operational processes, governance, stakeholder engagement and efficiencies, and explain how these will inform the design and delivery of Phase III.

- Describe how Phase III will track both quantitative KPIs and qualitative outcomes, such as cluster capability development, network effects and longer-term impacts.

- Confirm how compliance with State Aid and UK Subsidy Control requirements will be ensured.

Required Outputs and Deliverables

The consultant will be expected to deliver the following outputs to a high standard, within an agreed format and timeframe:

- A comprehensive written report detailing all findings from the economic appraisal. This report must include a section on each of the key tasks outlined above, with clear recommendations supported by evidence.

- The report should provide clear conclusions and recommendations for programme delivery, governance, management and commercial and financial viability, with a focus on improving outcomes and achieving value for money.

All deliverables should be produced to a professional standard and delivered by the agreed deadlines.

Evidence of robust analysis should underpin all recommendations to ensure credibility and support effective decision-making for the programme’s future.

# Timelines and Deliverables for

# (A) Interim Evaluation for the InterTradeIreland Synergy Programme Phase II

# Followed by

# (B) Economic Appraisal of the InterTradeIreland Synergy Programme Phase III

The execution of the assignments should follow the below timelines and expected deliverables:

- Interim Evaluation for the InterTradeIreland Synergy Programme Phase II

The delivery of the interim evaluation will require a commitment of resources according to the below timelines:

- Inception meeting will be held w/c 16th February, 2026

- Draft report of evaluation to be provided no more than 6 weeks after inception, w/c 23rd March 2026

- Final written evaluation report to be completed no more than 8 weeks after inception, by 10th April 2026.

(b) Economic Appraisal of the InterTradeIreland Synergy Programme Phase II

The delivery of the Economic Appraisal will require a commitment of resources according to the below timelines:

- Inception meeting will be held w/c 13th April 2026,

- Draft economic appraisal report to be provided no more than 6 weeks after inception, w/c 18th May 2026

- Final written economic appraisal report to be completed no more than 8 weeks after inception, w/c 1st June, 2026

The following deliverables and timeline are anticipated for these assignments:

- Inception Meeting: An initial meeting will be held (virtually or in person at InterTradeIreland’s offices) within the week the contract is awarded to refine the work plan and confirm information needs.

- Stakeholder Consultations: To be carried out in the early phase of the project (approximately weeks 1–3). InterTradeIreland will assist by providing relevant contacts and background materials.

- Review Meeting: An interim progress review meeting will be held with InterTradeIreland around the mid-point of the assignment to discuss preliminary findings and address any issues.

- Draft Report: A draft report must be submitted to InterTradeIreland for review by approximately week 6 of each assignment timeline. This draft will be reviewed by the Programme Team (and other stakeholders as appropriate). Upon delivery of the draft report, a meeting will be organised to discuss feedback and required revisions.

- Final Report: Final report of the assignment, incorporating feedback, is due by week 8 from date of assignment inception meeting (exact date to be confirmed at contract stage).

- Final Deliverable: The final deliverables are:

  - for assignment (A) a complete Interim Evaluation of Synergy Programme Phase II document (in Word and PDF format) ready for submission

  - for assignment (B) a complete Economic Appraisal of Synergy Programme Phase III document (in Word and PDF format) ready for submission.

InterTradeIreland will provide the consultant with all relevant background documentation, data, and contacts at the project outset to support the Interim Evaluation of InterTradeIreland Synergy Programme Phase II and Economic Appraisal of InterTradeIreland Synergy Programme Phase III (subject to normal confidentiality and GDPR restrictions). The consultant is expected to treat any sensitive information appropriately. Any technical analysis or detailed assumptions underlying the Interim Evaluation and Economic Appraisal should be documented clearly, with supporting data or calculations included in an annex to the report.

Throughout the assignment, the consultant should maintain regular communication with the InterTradeIreland project manager. The successful tenderer will be required to attend key meetings – including the initial meeting, an interim progress review, and a final presentation/review meeting – as part of the project delivery. These may be conducted on-site at InterTradeIreland or virtually, as agreed during project initiation.

Overall, the evaluations should be conducted in accordance with the Northern Ireland Guidance on evaluations, including Better Business Cases NI. (Supplementary evaluation guidance (finance-ni.gov.uk)) and the presentation of the appraisal should follow the sequence outlined in the scope of work and key stages sections of the TOR. Any technical or background information necessary to the appraisal and a list of the assumptions made should be included as an annex to the appraisal.

Submission and Administrative Details

- Clarifications: Any clarification questions regarding this tender must be submitted via email to tenders@intertradeireland.com by the 23rd January 2026 at 2pm. Responses to all queries will be compiled and published on InterTradeIreland’s website to ensure fairness and transparency.

- Tender Submission: Completed tender proposals must be submitted by email to tenders@intertradeireland.com no later than 5th February 2026 at 2pm. The submission must be in the format requested (as per format the requirements criteria detailed below) and include all required information. Late or incomplete submissions will not be considered.

- Contract Award: Contract award will be communicated by 12th February 2026, with the inception meeting held the following week.

Tender proposals should remain valid for a minimum of 90 days from the submission deadline.  The successful bidder will be required to enter into a contract for services with InterTradeIreland and commence work immediately upon award (timeline adjustments can be discussed to accommodate any lead-in if necessary).

InterTradeIreland reserves the right to modify the terms, or to cancel or re-issue this Request for Tender at any time, at its sole discretion. InterTradeIreland is not bound to accept the lowest cost or any proposal submitted. All costs incurred in the preparation of the tender response are the responsibility of the bidder.

Format and Requirements

Tenderers are required to submit the below detail to ensure a fully compliant proposal:

- Proposals should be delivered in word document format, with response length corresponding to the Award Criteria outlined in stage 2 of the Evaluation Criteria.

- Tenderers should include, at a minimum, the below documentation (in the order desired by the tenderer):

  - Evidence of Fair Work Practice

  - Proposed Personnel (Appendix A, B and C)

  - Tender proposal laid out according to Award Criteria (see Stage 2 of Evaluation Criteria)

  - Cost Schedule (Appendix D)

  - VAT Registration (Appendix E)

  - Declaration and Undertaking (Appendix F)

  - Certificate relating to Bona Fide Tender (Appendix G)

  - Form of Tender (Appendix H)

Cost & Payment

All tenders should include a detailed schedule of costs on the attached form “Cost Schedule”. It is anticipated that the combined cost of these assignments (a) and (b) will not exceed £45,000 excluding VAT. However, tenderers are advised that this is a competition and should price their bids accordingly.

Payment will be made as follows:

- On satisfactory completion of draft report (A) Interim Evaluation of the InterTradeIreland Synergy Programme Phase II (25% of the contract price).

- Following approval by InterTradeIreland of the final report (A) Interim Evaluation for the InterTradeIreland Synergy Programme Phase II (25% of the contract price).

- On satisfactory completion of draft report (B) Economic Appraisal of the InterTradeIreland Synergy Programme Phase III (25% of the contract price).

- Following approval by InterTradeIreland of the final report (B) Economic Appraisal of the InterTradeIreland Synergy Phase III Programme and all government Departments (25% of the contract price).

Evaluation Criteria

InterTradeIreland evaluate tenders in 2 stages:

- Stage 1 - Selection Criteria (SC)

- Stage 2 – Award Criteria (AC)

- Stage 1 - Selection Criteria – Fair Work Practices / Technical or Professional Ability – Pass/Fail

Fair Work Practices

The Executive and NICS Departments are committed to the delivery of high-quality public services and recognise that this is critically dependent on a workforce that is well rewarded, well-motivated, and has access to appropriate opportunities for training and skills development.

To ensure the highest standards of service quality in this contract we expect contractors to take a similarly positive approach to fair work practices.

This should include:

- clear managerial responsibility to nurture talent and help individuals fulfil their potential, including for example, promoting equality of opportunity and developing a workforce which reflects characteristics such as age, gender, religion or belief, race, sexual orientation and disability;

- support for learning and development;

- stability of employment and hours of work, and avoiding exploitative employment practices, including for example no inappropriate use of zero hours contracts; and

- support progressive workforce engagement, for example Trade Union recognition and representation where possible, otherwise, alternative arrangements to give staff an effective voice.

- a fair and equal pay policy that includes a commitment to supporting the Living Wage, including, for example being a Living Wage Accredited Employer

Please see Annex A for further details.

| SC1 | Fair Work Practices Tenderers must provide evidence of their positive approach to fair work practices. Please describe your policies, which provide fair work practices for workers (including any agency or sub-contractor workers) engaged in the delivery of this contract. Where an Economic Operator(s) is classified and operates as a sole trader the ‘Fair Work Strategy’ criteria will not apply. Tenderers should clearly evidence this in their response to the criteria. | Pass/Fail |
| --- | --- | --- |
| SC2 | Proposed Team Experience The Tenderer must clearly identify a minimum of 2 key individuals within the assignment i.e. 1) Project Manager and 2) Senior Consultant. Appendix A and B must be fully completed for these members of the project team as appropriate. The Project Manager and Senior Consultant(s) must demonstrate that they meet the following minimum standards of technical or professional ability as applicable to their role and as identified in this tender document. - Project Manager (1 named individual only) must have - Practical experience of working with government-level economic development agencies. - Knowledge of similar economic development programmes. - Knowledge of current and planned economic government policies and strategies. - Experience and knowledge of conducting evaluations. - Two separate relevant examples should be given where the Project Manager has led a project team to complete an evaluation or appraisal of a government funded business development or innovation programme within the last 3 years. - Senior Consultant (may have more than 1 named individual) must have - Practical experience of working with government-level economic development agencies. - Knowledge of similar economic development programmes. - Knowledge of current and planned economic government policies and strategies. - Experience and knowledge of conducting evaluations. - Two separate relevant examples should be given where the Senior Consultant has played a key role in carrying out an evaluation or appraisal of a government funded business development or innovation programme within the last 3 years. Responses (per person) contained within Appendix A & B must not exceed 2 sides of an A4 page – Font size Arial 11. Anything in excess of this page limit will not be evaluated. - Additional staff members – please name any other staff that will carry out administration duties on the evaluation by completing Appendix C. Please also specify their input in Appendix D – Cost Schedule. Tenderers should note that ‘within the last 3 years’ refers to within 3 years from the closing date of this tender competition. Projects that are currently ongoing and are not yet completed are permitted provided that the Tenderer can demonstrate that the required experience has been achieved, and the start date is included. The evaluation panel will make a decision based on the combined experience of all proposed personnel. | Pass/Fail |

Pass / Fail: – is defined as;

- Pass – Where the tenderer has fully demonstrated their ability to meet the minimum standard; and

- Fail – Where the tenderer has failed to fully demonstrate their ability to meet the minimum standard.

- Stage 2 – Award Criteria

All tenderers who pass Stage 1 will have their tenders assessed against the qualitative criteria (Award Criteria AC1 – AC4) and quantitative criteria (Award Criteria AC5) listed within this section. Tenderers must address each criterion fully.

The relative scoring of the award criteria is as follows:

- Qualitative Criteria (Quality) – 70%

- Quantitative Criteria (Cost) –   30%

2.1	Qualitative Criteria

Proposals must respond to each criterion separately by providing a detailed methodology that addresses the Objectives, Scope of Work and Key Tasks, and Required Outputs for (A) Interim Evaluation of InterTradeIreland Synergy Programme Phase II and/or (B) Economic Appraisal of InterTradeIreland Synergy Programme Phase III.

Responses for each Award Criterion must be contained in clearly marked sections for AC-1 - AC-4.  Any information submitted outside clearly marked sections will not be evaluated.

| Qualitative Criteria |  | Weight | Maximum Score |
| --- | --- | --- | --- |
| AC1 | [AC1], Proposed Methodology for Interim Evaluation of Synergy Programme Phase II (A) Tenderers must detail their proposed methodology for delivering the key stages of the interim evaluation as outlined in key stage section of the TOR, and detail how they will allocate resources to ensure delivery within the required timescale. This should clearly demonstrate the proposed methodology for (A) Interim Evaluation of InterTradeIreland Synergy Phase II Responses for this Award Criterion must not exceed 8 sides of an A4– Font size Arial 11. Anything in excess of this page limit will not be evaluated. | 25% | 100 |
| AC2 | [AC2], Proposed Methodology for Economic Appraisal of Synergy Programme Phase III (B) Tenderers must detail their proposed methodology for delivering the key stages of the economic appraisal as outlined in key stage section of the TOR, and detail how they will allocate resources to ensure delivery within the required timescale. This should clearly demonstrate the proposed methodology for (B) Economic appraisal of InterTradeIreland Synergy Phase III Responses for this Award Criterion must not exceed 8 sides of an A4 page– Font size Arial 11. Anything in excess of this page limit will not be evaluated. | 25% | 100 |
| AC3 | [AC-3], Project Plan The plan must include key dates, goals and milestones to ensure delivery of this service. This should clearly demonstrate the plan for (A) Interim Evaluation of InterTradeIreland Synergy Phase II AND (B) Economic appraisal InterTradeIreland Synergy Phase III Responses for this Award Criterion must not exceed 4 sides of an A4 page– Font size Arial 11. Anything in excess of this page limit will not be evaluated. | 10% | 100 |
| AC4 | [AC4], Contract Management Tenderers must demonstrate how they propose to manage the Contract to ensure the provision of a high-quality service, which meets the requirements set out within the Specification. The response must detail what systems and processes will be in place to ensure the continuity of service in the event of unplanned events (e.g. staff absences, systems failure etc.) and the procedures for escalation in the event that problems cannot be resolved at the operational level. Responses for this Award Criterion must not exceed 3 sides of an A4 page – Font size Arial 11. Anything in excess of this page limit will not be evaluated | 10% | 50 |
|  | TOTAL – QUALITATIVE AWARD CRITERIA | 70% | 350 |

Quantitative Criteria (Price)

|  | Weight | Maximum Score |
| --- | --- | --- |
| AC- 5 Price | 30% | 150 |
| Total | Weight | Maximum Score |
| Quality + Price | 100% | 500 |

Key to Scoring

To ensure consistency and equality the evaluation panel will assign scores for quality of response to the qualitative requirements using the scores and indicators below:

| Score | Descriptor |
| --- | --- |
| 0 | Failed to address the criterion. |
| 1 | Poor proposal to address the criterion. |
| 2 | Limited proposal to address criterion. |
| 3 | Acceptable proposal to address the criterion. |
| 4 | Good proposal to address the criterion. |
| 5 | Excellent proposal to address the criterion. |

If tenderers score 2, 1 or 0 in any of the qualitative criteria AC1 –AC3, then it shall be deemed that they have failed to meet the specification, and their tender will be eliminated from the competition.

2.2	Quantitative Assessment – Cost schedule

The Cost Schedule Appendix D must be completed. For those tenders passing the qualitative assessment, the following formula will be used to evaluate the total cost set out in Appendix D:

1.	Lowest price tendered will be awarded the maximum score available [150]

2.	To calculate the score for the remaining prices, the following formula will be applied. The lowest tendered price divided by the tenderer’s price multiplied by 150

3.	Where a zero cost or “no cost” offer is made this offer will be assigned a nominal 1 pence value for assessment purposes only.

Tenderers should note that InterTradeIreland is not obliged to accept the lowest or any tender.

Whilst every endeavour has been made to provide tenderers with an accurate description of the requirements, tenderers should form their own conclusions about the methods and resources needed to meet those requirements. InterTradeIreland cannot accept responsibility for tenderers’ assessment of the requirement.

Organisations that have been engaged or involved in the delivery of services to this Programme are precluded from tendering for this contract.

Annex A

WHAT GOOD FAIR WORK PRACTICE LOOKS LIKE

Good practice examples: equality of opportunity and diversity

- Clear managerial responsibility to nurture talent and help individuals fulfil their potential, including for example, promoting equality of opportunity and developing a workforce which reflects characteristics such as age, gender, religion or belief, race, sexual orientation and disability.

- Fair Work expects employers to go beyond their legal obligations under the Equality Act 2010, enhancing the protections for workers on the basis of their age, disability, gender reassignment, marriage and civil partnership, pregnancy and maternity, race, religion and belief, sex, and, sexual orientation.

- Employment can play a major part in addressing racial inequality. Through fair working practice, minority ethnic workers will be able to access and sustain employment commensurate with their skills, experience and/or employment goals and in working environments that are diverse and inclusive.

- Disabled people also experience discrimination and a lack of access to opportunity. We need to ensure our workplaces are not designed or operating in ways that can create barriers and exclude disabled people. Fair and equal access, and the provision of appropriate support, can greatly improve disabled people’s chances, enabling access to jobs, job retention and career progression.

Good practice examples: recruitment

- Recruitment, retention and promotion processes prevent bias and barriers, e.g. ’blind’ recruitment; providing any additional support/adjustments at interviews; diversity in interview panels; exit interviews are used to understand why a person is leaving.

- Workers have opportunities to influence the organisation’s approach to workplace equality, including by sharing their own experiences.

- The organisation gathers data to understand its workforce diversity and has a plan in place to address under-representation.

- Governance structures are gender balanced and the organisation is working to ensure parity for minority ethnic, disabled and younger people.

- Workplace adjustments are made for disabled staff who need it, e.g. Access to Work.

- Everyone has equal access to appropriate learning & development opportunities.

- All staff have opportunities to discuss their support needs with management.

- Employers are able to provide safe spaces for workers to express their concerns and raise issues and where workers are confident that their concerns are dealt with appropriately by trained personnel.

Good practice examples: support for learning and development

- Effective workforce development involves employers providing opportunities for their staff at all levels of the organisation and should be a shared responsibility and shared commitment between the employer and workers.

- Everyone should be able to engage in lifelong learning.

- Learning & development is integrated in the organisation’s strategic planning and workers, and management jointly identify development needs and priorities, ensuring both individual and organisational needs are met.

- Regular equality and diversity training is provided for all staff.

- Learning & development opportunities are provided, and regularly reviewed, to help build the organisation’s resilience and responsiveness to change.

- Formal and informal learning is offered across the workforce, relating to people’s particular role and wider development.

- The organisation is committed to providing apprenticeships.

Good practice examples: secure employment and avoiding exploitative employment practices, including for example no inappropriate use of zero hours contracts

- Although there is no legal definition of a zero-hours contract, in the context of Fair Work, such a contract is one which does not guarantee any work to the individual and does not set out a minimum number of hours (whether ongoing or for a set period). An employer is likely to be using a zero-hours contract inappropriately if:

- they offer a worker a regular pattern of work or regular number of hours but offer only a casual/zero-hours contract;

- a worker has had no say in the zero-hours contract and actually wants a contract of employment guaranteeing a minimum number of hours;

- they put pressure on a worker to accept the terms of a zero-hours contract (where challenged) in order to keep their job;

- there is an expectation that workers will accept all hours offered but no reciprocal expectation that the employer will guarantee hours of work.

- Employers using zero-hours contracts should be able to credibly explain their exceptional circumstance which leads to them using such contracts and the steps they are taking to review their business model to eliminate these circumstances.

- All staff are employed on open-ended or fixed term contracts with confirmed hours and work pattern.

- All staff have a contract which accurately reflects the hours worked, guarantees a fair minimum number of hours per week and does not involve compulsory overtime.

- Staff get reasonable notice of shifts – at least 4 weeks ahead of time and are paid for cancelled shifts within this period.

- Core and flexible staff resources are reviewed at least annually to determine if any staff on a zero-hours or minimum-hours contract can be moved to a permanent or fixed-term contract with a fixed number of hours and/or a regular pattern.

- Zero-hours contracts are not used to the detriment of workers with protected characteristics and where this is happening, the organisation is taking remedial action.

- Zero-hours contracts are not used to fill actual longer-term vacancies.

- There is a clear, published policy and process to enable someone to request a move from a zero-hour contract with guaranteed and set hours.

Good practice examples: workforce voice and recognition

- Effective voice is much more than having a communication channel available within an organisation. It requires a safe environment where dialogue and challenge are central to the organisational culture, are dealt with constructively, and where employee views are sought out, listened to and acted upon, and can make a difference.

- Effective voice requires workers, employers and trade unions or worker representative groups to work in partnership to make sure the right decisions are made to ensure workers are treated fairly and equitably. The co-determination of working practices is key to delivering all of the dimensions of Fair Work effectively.

- Involving trade union/employee representatives in key governance and decision-making structures.

- Recognising trade unions for the purpose of collective bargaining and encouraging membership, where this is the workforce’s preferred route, and providing appropriate facility time for supporting regular engagement between union/s and members.

- Constructive dialogue between the employer, workers and where appropriate a relevant trade union/s to address workplace issues or disputes, e.g. absence management, grievance, health & safety.

- Regular surveys are carried out to understand worker views, including how well they feel effective voice is facilitated in the organisation, and are involved in agreeing and progressing improvement action.

- Appropriate collective consultation and a clear route for resolving issues at both individual and collective levels, such as through a grievance or collective disputes procedure.

- Dealing with issues/concerns which have been formally raised fairly in a timely and constructive manner, and which promotes confidence that, whatever the outcome, fair processes have supported fair resolution.

- Appropriate measures are in place to support dignity in the workplace and implement zero tolerance of workplace bullying and other forms of abuse and harassment.

APPENDIX A – ROLE WITHIN THIS ASSIGNMENT: PROJECT MANAGER

NAME: POSITION WITHIN ORGANISATION:

SPECIFIC EXERIENCE

- The Project Manager must have practical experience of working with government-level economic development agencies.

- Knowledge of similar economic development programmes:

- Knowledge of current and planned government economic policies and strategies:

- Experience and knowledge in conducting evaluations or appraisals.

Two relevant examples should be given where the Project Manager has led a project team to complete an evaluation or appraisal of at least 2 government funded business development or innovation programmes within the last 3 years. NB: Three years is defined as 3 years from the closing dated stated on this tender document. Example 1 Client: Assignment: Date Completed: Description of Assignment and its relevance:

Example 2 Client: Assignment: Date Completed: Description of Assignment and its relevance:

Responses (per person) contained within this Appendix must not exceed 2 sides of an A4 page– Font size Arial 11. Anything in excess of this page limit will not be evaluated.

APPENDIX B – ROLE WITHIN THIS ASSIGNMENT: SENIOR CONSULTANT

NAME: POSITION WITHIN ORGANISATION:

SPECIFIC EXERIENCE

- The Senior Consultant must have practical experience of working with government-level economic development agencies:

- Knowledge of similar economic development programmes:

- Knowledge of current and planned government economic policies and strategies:

- Experience and knowledge of conducting evaluations or appraisals.

Two relevant examples should be given where the Senior Consultant has played a key role in carrying out an evaluation or appraisal of at least 2 government funded business development or innovation programmes within the last 3 years. NB: Three years is defined as 3 years from the closing dated stated on this tender document. Example 1 Client: Assignment: Date Completed: Description of Assignment and its relevance:

Example 2 Client: Assignment: Date Completed: Description of Assignment and its relevance:

Responses (per person) contained within this Appendix must not exceed 2 sides of an A4 page– Font size Arial 11. Anything in excess of this page limit will not be evaluated.

APPENDIX C – ADDITIONAL STAFF MEMBERS

NAME: POSITION WITHIN ORGANISATION:

ROLE WITHIN THIS ASSIGNMENT INCLUDING DUTIES:

Responses (per person) contained within this Appendix must not exceed 1 side of an A4 page– Font size Arial 11.

APPENDIX D –COST SCHEDULE

TOTAL ASSIGNMENT COST

| Total Assignment Cost | £ |
| --- | --- |

The proposed total cost of the assignment should be stated in £ Sterling and should be exclusive of VAT but inclusive of all costs and overheads associated with delivering the Services under the Contract

BREAKDOWN OF COSTS AND DAYS

| Activity | Resource Name | Number of Days | Daily Rate | Cost £ (Sterling) (excl VAT) |  |
| --- | --- | --- | --- | --- | --- |
|  | Total Cost |  |  |  |  |

Appendix E - VAT

VAT REGISTRATION

Part 1 or Part 2 to be completed as appropriate by the Tenderer and returned at the time of tendering.

1.	My/Our VAT Registration Number is ________________________________

Signed by ______________________________________________________

For and on behalf of ______________________________________________

______________________________________________

______________________________________________

Date ________________________________________________________________

- I/We are “EXEMPT” from VAT under the terms of the Finance Act 1972.

Signed _____________________________________________________

For and on behalf of __________________________________________

__________________________________________

__________________________________________

Date ________________________________________________________________

Appendix F

DECLARATION AND UNDERTAKING TO BE SIGNED BY ALL MAIN CONTRACTORS, NOMINATED SUB-CONTRACTORS OR CONSULTANTS TENDERING FOR THE EXECUTION OF WORKS OR THE SUPPLY OF GOODS OR SERVICES AND MUST BE RETURNED AT THE TIME OF TENDERING

FAIR EMPLOYMENT AND TREATMENT (NORTHERN IRELAND) ORDER 1998

- Article 64 of the Fair Employment and Treatment (Northern Ireland) Order 1998 provides inter alia that a public authority shall not accept an offer to execute any work or supply any goods or services where the offer is made by an unqualified person in response to an invitation by the public authority to submit offers.  Article 64(4) also provides that the public authority shall take all such steps as are reasonable to secure that no work is executed or goods or services supplied for the purposes of such contracts as are mentioned above by an unqualified person.

- For the purposes of Articles 64 – 66 of the Order, an unqualified person is a person on whom a notice has been served under Article 62(2) or Article 63(1) of the Order and which has not been cancelled.

- Mindful of its obligations under the Order, InterTradeIreland has decided that is shall be a condition of tendering that a contractor shall not be an unqualified person for the purpose of Articles 64 – 66 of the Order.

- Contractors are therefore asked to complete and return the form endorsed hereon, with their tender, to confirm that they are not unqualified persons and to undertake that no work shall be executed or goods or services supplied by an unqualified person for the purposes of any contract with InterTradeIreland to which Article 64 of the Order applies.

FAIR EMPLOYMENT AND TREATMENT (NORTHERN IRELAND) ORDER 1998

I/We hereby declare that I am/we are not unqualified for the purposes of the Fair Employment and Treatment (Northern Ireland) Order 1998.

I/We undertake that no work shall be executed or goods or services supplied by any unqualified person for the purposes of any contract with InterTradeIreland to which Article 64 of the Order applies.

Signed by: _____________________________

Duly authorised to sign for and on behalf of: ____________________________

Date:  ______________________

Appendix G

CERTIFICATE RELATING TO BONA FIDE TENDER

- The essence of tendering is that the client shall receive bona fide competitive tenders from all firms tendering.  In recognition of this principle, we certify that this is a bona fide tender intended to be competitive and that we have not fixed or adjusted the amount of the tender by or under or in accordance with any agreement or arrangements with any other person.

- We also certify that we have not:

  - Communicated to a person other than the person calling for these tenders the amount or approximate amount of the proposed tender, except where the disclosure, in confidence, of the approximate amount of the tender was necessary to obtain insurance premium quotations required for the preparation of this tender;

  - Entered into any agreement or arrangement with any other person that he shall refrain from tendering or as to the amount of any tender to be submitted;

  - Offered or paid or given or agreed to pay or give any sum of money or valuable consideration directly or indirectly to any person for doing or having done or causing or having caused to be done in relation to any other tender or proposed tender for the said work any act or thing of the sort described above

- We undertake that we will not do any of the acts mentioned in paragraphs 2a, 2b or 2c above at any time before the acceptance or rejection of this tender.

- In this certificate the word “person” includes any persons and anybody or association corporate or unincorporate any “any agreement or arrangement” includes any such transaction, formal or informal and whether legally binding or not.

Signed:

BLOCK CAPITALS: ______________________________

For and on behalf of:  _____________________________

Date: __________________________________________

Appendix H

FORM OF TENDER

TO BE COMPLETED BY THE TENDERER AND RETURNED AT THE TIME OF TENDERING

CONTRACT FOR

_________________________________________________________________

- I/We the undersigned hereby tender for the above contract in accordance with the Te4rms of Reference at the prices quoted in the Schedule forming part of my/our tender response.

- I/We declare there would be no conflict of interest or perceived conflict of interest in relation to the personnel or type of work involved in this contract.

- I/We agree that this Tender together with your written acceptance thereof shall constitute a binding contract between us in relation to the whole or such part of the Tender as may be specified in your written acceptance.

- I/We accept and agree to abide by the Terms of Reference requirements which take precedence over any terms, conditions, stipulations or provisos which may appear on or be annexed to any correspondence submitted by me/us in connection with this Contract.

- I/We understand that ITI does not bind itself to accept the lowest or any tender submitted in response to this enquiry and may accept the whole or part of any tender.

- I/We understand that the acceptance of any Tenders will be on the basis of the published evaluation criteria.

- I/We understand that the acceptance of this Tender does not bind ITI to place any orders under it and that the ITI may accept more than one Tender for the supply of the service covered by this Tender.

- I/We understand the ITI reserves the right to discontinue the award procedure in the event of irregular tenders or in the absence of appropriate tenders and in such circumstances may use the negotiated procedure without a further call for competition.

- I/We warrant that I/we have all the requisite corporate authority to sign this tender.

Dated this _____________________ day of ________________________________

Signed by or on behalf of the Tenderer:     __________________________________

Name of Tenderer:	__________________________________________________

(BLOCK CAPITALS)

Registered Address:	__________________________________________________

__________________________________________________

__________________________________________________

____________________________